BUSINESS REQUIREMENTS DOCUMENT

Endpoint Migration: Legacy REST to gRPC Transaction Service

| Document ID | BRD-TXN-2025-004 |
| --- | --- |
| Project | Transaction Service Endpoint Migration |
| Version | 1.0.0 |
| Status | APPROVED |
| Date | June 2025 |
| Author | Platform Engineering Team |
| Reviewed By | CTO, VP Engineering, Security |
| Classification | Confidential – Internal Only |

# 1. Executive Summary

This Business Requirements Document (BRD) defines the functional and non-functional requirements for migrating the Transaction Processing Service from the legacy REST/HTTP v1 endpoint to a high-performance gRPC-based v2 endpoint. The migration is driven by scalability constraints, payload serialization overhead, and the need for bidirectional streaming capabilities demanded by real-time financial transaction workloads.

The existing endpoint (/api/v1/transaction) has reached its operational ceiling, exhibiting latency spikes under peak load and lacking strong contract enforcement via IDL. The new endpoint leverages Protocol Buffers and gRPC to achieve reduced serialization overhead, strict schema enforcement, and native support for server-side streaming.

## 1.1 Migration Goals

- Replace the legacy JSON/REST endpoint with a gRPC endpoint backed by Protobuf schemas

- Achieve ≥40% reduction in average request latency under production-level load

- Enable strict contract enforcement using .proto IDL definitions

- Support backward compatibility via a dual-run transition period

- Ensure zero financial data loss during cutover

## 1.2 Scope

In scope:

- Migration of POST /api/v1/transaction → TransactionService.ProcessTransaction (gRPC)

- Migration of GET  /api/v1/transaction/{id} → TransactionService.GetTransaction (gRPC)

- Migration of GET  /api/v1/transaction/status → TransactionService.StreamTransactionStatus (gRPC server-stream)

- Client SDK updates (Go internal SDK v2)

- Canary rollout, monitoring, and rollback plan

Out of scope:

- Batch transaction endpoints (addressed in BRD-TXN-2025-005)

- External third-party consumer migration (handled by API Gateway translation layer)

# 2. Background & Problem Statement

## 2.1 Current State – Legacy Endpoint

The current Transaction Service exposes a REST/HTTP/1.1 API that has been in production since 2021. As transaction volumes grew 3× over 18 months, the following deficiencies have been observed:

| Issue | Observed Impact | Severity |
| --- | --- | --- |
| JSON serialization overhead | 18–25 ms added per request at p99 | HIGH |
| No streaming support | Polling loops, excess network calls | HIGH |
| Weak schema enforcement | Malformed payloads reach business logic | MEDIUM |
| HTTP/1.1 head-of-line blocking | Throughput degradation at >5k req/s | HIGH |
| No native deadline propagation | Timeout mismatches across service calls | MEDIUM |
| Manual versioning (URL segments) | Fragile contract evolution | LOW |

## 2.2 Target State – gRPC Endpoint

The new gRPC service will be defined via Protocol Buffers 3, served over HTTP/2, and exposed on port 50051 (internal) with mutual TLS. The service will be registered in the internal service mesh and will support:

- Unary RPC for individual transaction processing

- Server-side streaming for real-time status updates

- Interceptor-based auth, logging, and rate limiting

- Deadline and cancellation propagation natively via context

## 2.3 Decision Drivers

- Performance SLA tightened to p99 < 50 ms for ProcessTransaction

- Compliance requirement for strongly-typed audit trails

- Platform standardization on gRPC for all internal service-to-service calls

- Upcoming real-time fraud detection requires streaming transaction feed

# 3. Stakeholder Analysis

| Stakeholder | Role | Interest Level | Influence |
| --- | --- | --- | --- |
| CTO | Executive Sponsor | High | High |
| VP Engineering | Project Owner | High | High |
| Platform Team (Backend) | Implementer | High | High |
| Mobile / Frontend Teams | Consumer (SDK update) | Medium | Medium |
| Security & Compliance | Reviewer / Approver | High | High |
| QA Engineering | Validation | Medium | Medium |
| SRE / Ops | Deployment & Rollback | High | High |

# 4. Functional Requirements

## 4.1 Protobuf Service Definition

The following service contract must be implemented and registered in the internal proto repository:

syntax = "proto3";

package transaction.v2;

option go_package = "github.com/fintech/transaction/v2";

service TransactionService {

  rpc ProcessTransaction (TransactionRequest) returns (TransactionResponse);

  rpc GetTransaction     (GetTransactionRequest) returns (TransactionResponse);

  rpc StreamStatus       (StreamStatusRequest)   returns (stream StatusUpdate);

}

## 4.2 Endpoint Mapping

| Legacy REST Endpoint | HTTP Method | gRPC Method | RPC Type |
| --- | --- | --- | --- |
| /api/v1/transaction | POST | TransactionService.ProcessTransaction | Unary |
| /api/v1/transaction/{id} | GET | TransactionService.GetTransaction | Unary |
| /api/v1/transaction/status | GET | TransactionService.StreamStatus | Server Stream |

## 4.3 Request / Response Field Mapping

| Legacy JSON Field | Proto Field | Type | Required | Notes |
| --- | --- | --- | --- | --- |
| transaction_id | transaction_id | string | Yes | UUID v4 |
| amount | amount | int64 | Yes | In minor currency units (cents) |
| currency | currency_code | string | Yes | ISO 4217 (3-char) |
| source_account | source_account_id | string | Yes | Internal account UUID |
| dest_account | dest_account_id | string | Yes | Internal account UUID |
| timestamp | created_at | Timestamp | Yes | google.protobuf.Timestamp |
| metadata | metadata | map<string,string> | No | Arbitrary KV pairs |
| status | status | TxStatus | Resp | Enum: PENDING/SUCCESS/FAILED |

## 4.4 Error Handling

All errors must be returned using standard gRPC status codes. The following mapping from legacy HTTP codes applies:

| HTTP Status | gRPC Status Code | Use Case |
| --- | --- | --- |
| 400 Bad Request | INVALID_ARGUMENT | Malformed request payload |
| 401 Unauthorized | UNAUTHENTICATED | Missing or invalid auth token |
| 403 Forbidden | PERMISSION_DENIED | Insufficient permissions |
| 404 Not Found | NOT_FOUND | Transaction ID does not exist |
| 409 Conflict | ALREADY_EXISTS | Duplicate transaction submission |
| 429 Too Many Req | RESOURCE_EXHAUSTED | Rate limit exceeded |
| 500 Server Error | INTERNAL | Unexpected server-side failure |
| 503 Unavailable | UNAVAILABLE | Downstream service down |

# 5. Non-Functional Requirements

## 5.1 Performance

| Metric | Current (REST) | Target (gRPC) | Measurement |
| --- | --- | --- | --- |
| p50 latency (ProcessTransaction) | 12 ms | < 6 ms | Prometheus histogram |
| p99 latency (ProcessTransaction) | 85 ms | < 50 ms | Prometheus histogram |
| Throughput (peak) | 5,200 RPS | ≥ 12,000 RPS | Load test (k6) |
| Payload size (avg request) | ~2.1 KB | < 600 bytes (proto) | Network capture |
| Error rate (5xx equivalent) | 0.08% | < 0.02% | Prometheus counter |

## 5.2 Security

- All gRPC traffic MUST use mutual TLS (mTLS) with certificates issued by the internal PKI

- JWT-based authentication must be validated via a gRPC interceptor before reaching business logic

- Transaction payloads must not be logged at DEBUG level; only transaction_id and status are permissible in logs

- Rate limiting: 1,000 RPM per authenticated client, enforced at the interceptor layer

## 5.3 Reliability

- Service availability target: 99.95% monthly SLA

- Graceful degradation: gRPC server must return UNAVAILABLE rather than hang when downstream DB is unreachable

- Idempotency: ProcessTransaction must be idempotent on transaction_id (duplicate requests return the cached response)

- Health check: gRPC health protocol (grpc.health.v1.Health) must be implemented for load balancer probes

## 5.4 Observability

- All RPCs must emit OpenTelemetry spans with service.name = transaction-service-v2

- Prometheus metrics: grpc_server_handled_total, grpc_server_handling_seconds (histogram)

- Structured JSON logs (zerolog) with trace_id, span_id, transaction_id on every log line

# 6. Migration & Rollout Plan

## 6.1 Migration Strategy: Strangler Fig + Canary

The migration will follow a Strangler Fig pattern. The API Gateway will route traffic between the legacy and new endpoints based on feature flags. A canary rollout will increase gRPC traffic incrementally while monitoring error rates and latency.

## 6.2 Phased Rollout

| Phase | Description | Traffic Split (gRPC) | Duration | Exit Criteria |
| --- | --- | --- | --- | --- |
| Phase 0 – Prep | Proto schema review, SDK release, staging deploy | 0% | 2 weeks | All tests green, perf benchmarks met |
| Phase 1 – Shadow | gRPC receives shadow copy of all requests | 0%+shadow | 1 week | No unexpected errors in shadow logs |
| Phase 2 – Canary | 5% live traffic routed to gRPC endpoint | 5% | 1 week | Error rate < 0.02%, p99 < 50 ms |
| Phase 3 – Ramp | 25% → 50% → 75% over 3 days each | 75% | 2 weeks | SLA targets maintained at each step |
| Phase 4 – Full | 100% traffic on gRPC, legacy on standby | 100% | 1 week | Zero incidents for 7 days |
| Phase 5 – Cleanup | Decommission legacy endpoint and infrastructure | 100% | 1 week | Runbook verified, monitoring updated |

## 6.3 Rollback Procedure

- Trigger: p99 > 150 ms OR error rate > 0.1% for > 5 consecutive minutes

- Action: Feature flag flip routes 100% traffic back to legacy REST endpoint within 30 seconds

- Notification: PagerDuty alert fires, incident bridge opened

- Root cause analysis required within 24 hours before re-attempting canary

# 7. Acceptance Criteria

| ID | Requirement | Acceptance Test | Pass Condition |
| --- | --- | --- | --- |
| AC-01 | ProcessTransaction RPC operational | Integration test: valid payload | Response status = SUCCESS, latency < 50 ms |
| AC-02 | GetTransaction RPC operational | Integration test: existing txn_id | Correct transaction returned |
| AC-03 | StreamStatus RPC operational | Stream 10 status updates | All 10 received in order, no timeout |
| AC-04 | mTLS enforced | Send without cert → expect UNKNOWN | Connection rejected |
| AC-05 | Invalid payload → INVALID_ARGUMENT | Send malformed proto message | gRPC status INVALID_ARGUMENT returned |
| AC-06 | Duplicate txn_id idempotent | Send same txn_id twice | Second call returns cached response |
| AC-07 | p99 < 50 ms under load | k6 load test: 10k RPS for 10 min | p99 histogram ≤ 50 ms |
| AC-08 | Throughput ≥ 12,000 RPS | k6 load test: ramp to 15k RPS | Service sustains 12k RPS, error < 0.02% |
| AC-09 | OTel traces emitted | Jaeger trace query during test | Spans visible with correct attributes |
| AC-10 | Rollback < 30 seconds | Toggle feature flag off | 100% traffic on legacy within 30 s |

# 8. Risk Register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| SDK version mismatch in downstream consumers | Medium | High | Publish SDK v2 2 weeks before Phase 2; provide migration guide |
| Proto schema breaking change mid-migration | Low | High | Schema lock after Phase 0; all changes via additive evolution only |
| Load balancer not supporting gRPC (HTTP/2) | Low | Medium | Validate LB config in staging; document HAProxy/Envoy settings |
| mTLS cert rotation outage | Low | High | Implement cert hot-reload; 30-day overlap on cert validity |
| Unexpected data format incompatibility (amounts) | Medium | High | Unit tests comparing REST JSON vs proto encoded values before go-live |
| OTel collector bottleneck at high throughput | Medium | Medium | Batch export, async channel; load test collector independently |

# 9. Project Timeline

| Milestone | Owner | Target Date | Status |
| --- | --- | --- | --- |
| Proto schema finalized & reviewed | Platform Eng | Week 1 | DONE |
| Go server skeleton + unit tests | Platform Eng | Week 2 | DONE |
| Interceptor chain (auth, logging, RL) | Platform Eng | Week 3 | IN PROGRESS |
| Internal SDK v2 published | Platform Eng | Week 3 | IN PROGRESS |
| Staging deployment + integration tests | QA + SRE | Week 4 | PLANNED |
| Load testing (k6 benchmarks) | SRE | Week 5 | PLANNED |
| Security review + pen test | Security | Week 5 | PLANNED |
| Phase 1 (Shadow) begin | SRE | Week 6 | PLANNED |
| Phase 2–3 (Canary + Ramp) | SRE + Platform | Week 7–9 | PLANNED |
| Phase 4 (100% gRPC) | SRE | Week 10 | PLANNED |
| Legacy endpoint decommission | Platform + SRE | Week 11 | PLANNED |

# 10. Appendix

## A. Key Proto Message Definitions

message TransactionRequest {

  string transaction_id    = 1;

  int64  amount            = 2;

  string currency_code     = 3;

  string source_account_id = 4;

  string dest_account_id   = 5;

  google.protobuf.Timestamp created_at = 6;

  map<string, string> metadata = 7;

}

message TransactionResponse {

  string    transaction_id = 1;

  TxStatus  status         = 2;

  string    message        = 3;

  google.protobuf.Timestamp processed_at = 4;

}

enum TxStatus { PENDING = 0; SUCCESS = 1; FAILED = 2; }

## B. Related Documents

- BRD-TXN-2025-001: Transaction Service Architecture Overview

- BRD-TXN-2025-003: Auth Interceptor Design Specification

- SRE-RB-042: Endpoint Migration Runbook

- SEC-2025-017: mTLS Certificate Management Policy

## C. Approval Sign-off

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| CTO | — | ______________________ | ___________ |
| VP Engineering | — | ______________________ | ___________ |
| Security Lead | — | ______________________ | ___________ |
| Project Manager | — | ______________________ | ___________ |

— END OF DOCUMENT —